## Team
Initials | First | Last | Email | GitHub Username
yw | Yanjun | Wu | ywu29@stevens.edu | LSYanJun
gc | Gong | Cheng | gcheng2@stevens.edu | chenggongtc
abg | Amog | bheemanakolli gurumallappa | abheeman@stevens.edu | amoghagurumallappa
|  |  | GitHub Repository: | SSW555tm052015s

## Backlog
Sprint | Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Added
1 | US01 | Inexistent ID | AT01~AT07 | gc | Done | 150 | 60 | 98 | 60 | 2015-02-27 | 2015-02-25
1 | US02 | Unmatched pointers | AT08~AT14 | gc | Done | 50 | 40 | 72 | 45 | 2015-02-28 | 2015-02-25
| US03 | [9 empty] | 2014-10-10
US04
US05
US06
US07
US08
US09
US10
US11
US12
US13
US14
US15
US16
US17
US18
US19
US20
US21
US22
US23
US24
US25

## Stories
Story ID | Story Name | Story Description | Acc Tests | Est Size | Est Time
US01 | Inexistent ID | Make sure that the ID of an individual in a family or the ID of a family of an individual exists | AT01~AT07 | 150 | 60
US02 | Unmatched pointers | Make sure that the pointers of an individual matches the pointers of the related families, and vice versa | AT08~AT14 | 50 | 40
US03 | Invalid date | Make sure that all the dates are before today
US04 | Invalid family members | A family must contain a husband and a wife
US05 | Death before birth | Make sure that an individual's death date is >= their birth date
US06 | Invalid gender | Make sure that in a family, father is a male and mother is a female
US07 | Invalid age of an individual | Make sure that an individual's age is between 0 and 150
US08 | Multiple roles in a family | Make sure an individual can play only one role in a family
US09 | Invalid ages in a family | Make sure that the parents are older than children in one family
US10 | Death before marriage | Make sure that an individual's death date is >= their marriage date
US11 | Marriage before birth | Make sure that an individual's marriage date is >= their birth date
US12 | Divorce before marriage | Make sure that an individual's divorce date is >= their marriage date
US13 | Death before giving birth | Make sure that in a family, mother's death date is >= her children's birth dates and father's death date + 10 months is >= his children's birth dates
US14 | Monogamy | An individual can have at most one spouse
US15 | Illegal spouse | An individual can't marry to their sibling unless they are not biologically related
US16 | Illegal marrige age | A man can't get married until 20, a woman can't get married until 18
US17 | Amount of family members | A family can have at most 8 members
US18 | Age gap among the children | There should be at least 1 year age difference unless they were born on the same day
US19 | Pregnancy limit | Wife can give birth between the age of 18 and 50
US20 | Child in family | A person could be a child of only one family
US21 | Family rule | A person should be linked to at least one family
US22
US23
US24
US25
US26
US27

## Tests
AT ID | Story ID | Story Name | Input | Expected Output | Status
AT01 | US01 | Inexistent ID | Individual I1(Jacky /Mao/) is the child of F22 | Error message " Individual I1(Jacky /Mao/) is a child of an inexistent Family F22." | Passed
AT02 | US01 | Inexistent ID | Individual I3(Katie /Brown/) is the spouse of Family F23 | Error message " Individual I3(Katie /Brown/) is a spouse of an inexistent Family F23." | Passed
AT03 | US01 | Inexistent ID | Family F1's husband is Individual I18 | Error message " Family F1 has a husband who is an inexistent Individual I18." | Passed
AT04 | US01 | Inexistent ID | Family F2 has a child who is Individual I15 | Error message " Family F2 has a child who is an inexistent Individual I15." | Passed
AT05 | US01 | Inexistent ID | Family F3's wife is Individual I31 | Error message " Family F3 has a wife who is an inexistent Individual I31." | Passed
AT06 | US01 | Inexistent ID | Individual I5(Emily /Mao/) is the child of F2 and the spouse of F5 | No error message | Passed
AT07 | US01 | Inexistent ID | Family F4's husband is Individual I8(Kevin /Brown/), wife is Individual I9(Elena /Wilson/) and child is Individual I3(Katie /Brown/) | No error message | Passed
AT08 | US02 | Unmatched pointers | Individual I1(Jacky /Mao/) is one of the spouse of Family F1, and Family F1's husband is Individual I18 and wife is Individual I12 | Error message " Individual I1(Jacky /Mao/) is a spouse of Family F1, but Family F1 does not have the spouse of I1(Jacky /Mao/)." | Passed
AT09 | US02 | Unmatched pointers | Individual I3(Katie /Brown/) is one of the spouse of Family F3, and Family F3's husband is Individual I4 and wife is Individual I31 | Error message " Individual I3(Katie /Brown/) is a spouse of Family F3, but Family F3 does not have the spouse of I3(Katie /Brown/)." | Passed
AT10 | US02 | Unmatched pointers | Individual I5(Emily /Mao/) is one of the child of Family F2, and Family F2's children are I1 and I15 | Error message " Individual I5(Emily /Mao/) is a child of Family F2, but Family F2 does not have the child of I5(Emily /Mao/)." | Passed
AT11 | US02 | Unmatched pointers | Family F2's wife is Individual I3(Katie /Brown/), I3(Katie /Brown/) is the spouse of F23 and F3 | Error message " Family F2's wife is Individual I3(Katie /Brown/), but Individual I3(Katie /Brown/) is not the wife of Family F2." | Passed
AT12 | US02 | Unmatched pointers | Family F2 has a child who is Individual I1(Jacky /Mao/), and I1(Jacky /Mao/) is the child of F22 | Error message " Family F2 has a child who is Individual I1(Jacky /Mao/), but Individual I1(Jacky /Mao/) is not a child of Family F2." | Passed
AT13 | US02 | Unmatched pointers | Individual I2(Jianguo /Mao/) is one of the spouse of Family F2, and Family F2's husband is Individual I2(Jianguo /Mao/) | No error message | Passed
AT14 | US03 | Unmatched pointers | Family F3's husband is Individual I4(Edwin /Moore/), and Individual I4(Edwin /Moore/) is one of the spouse of Family F3 | No error message | Passed

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2014-09-22 | 36 |  | 0
2014-10-05 | 30 | 6 | 250 | 120 | 125
2014-10-19 | 24 | 6 | 400 | 90 | 100
2014-11-02 | 12 | 12 | 800 | 150 | 160
2014-11-16 | 6 | 6 | 900 | 80 | 75
2014-11-30 | 0 | 6 | 1000 | 60 | 100

## Sprint1
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Inexistent ID | AT01~AT07 | gc | Done | 150 | 60 | 98 | 60 | 2015-02-27
T01.01 | Check the existance of family IDs of every individual |  | gc
T01.02 | Link the existant family IDs to the related families |  | gc
T01.03 | Check the existance of individual IDs of every family |  | gc
T01.04 | Link the existant individual IDs to the related individuals |  | gc
US02 | Unmatched pointers | AT08~AT14 | gc | Done | 50 | 40 | 72 | 45 | 2015-02-28
T02.01 | Check if the family pointers of an individual point back to the individual(as the same role in the family) |  | gc
T02.02 | Check if the individual pointers of a family point back to the family(as the same role in the family) |  | gc
Review Results
Keep doing:
Meet twice a week
Text everyone when you discover a problem
Avoid:
Forgetting to commit changes to GitHub

## Sprint2
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint3
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint4
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint5
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed