## Team
Initials | First | Last | Email | GitHub Username
yw | Yanjun | Wu | ywu29@stevens.edu | LSYanJun
hm | Harlan | Mills | hmills@stevens.edu | harlanmills
at | Alan | Turing | aturing@stevens.edu | enigmacracker
|  |  | GitHub Repository: | SSW555tm052015s

## Backlog
Sprint | Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Added
1 | US01 | Death before birth | AT01, AT02 |  | Done | 150 | 60 | 120 | 90 | 2014-09-24 | 2014-08-25
1 | US02 | Death before marriage | AT03, AT04 |  |  | 200 | 120 |  |  |  | 2014-08-25
3 | US03 | Marriage before birth | AT05, AT06 | [7 empty] | 2014-10-10
US04
US05
US06
US07
US08
US09
US10
US11
US12
US13
US14
US15
US16
US17
US18
US19
US20
US21
US22
US23
US24
US25

## Stories
Story ID | Story Name | Story Description | Acc Tests | Est Size | Est Time
US01 | Invalid date format | Make sure that the date is in the form of 1 JAN 1990
US02 | Invalid ID format | Make sure that the individual ID is in the form of @I1@ and the family ID is in the form of @F1@
US03 | Invalid date of birth or death | Make sure that an individual is born or dead before today
US04 | Invalid gender format | The gender should be either F or M
US05 | Invalid name format | The surname should be delimited by "/"s
US06 | Invalid family members | A family must contain a husband and a wife
US07 | Death before birth | Make sure that an individual's death date is >= their birth date
US08 | Invalid gender | Make sure that in a family, father is a male and mother is a female
US09 | Invalid age of an individual | Make sure that an individual's age is between 0 and 150
US10 | Multiple roles in a family | Make sure an individual can play only one role in a family
US11 | Inexistent ID | Make sure that the ID of an individual in a family or the ID of a family of an individual exists
US12 | Unmatched pointers | Make sure that the pointers of an individual matches the pointer of the related families, and vice versa
US13 | Invalid ages in a family | Make sure that the parents are older than children in one family
US14 | Death before marriage | Make sure that an individual's death date is >= their marriage date
US15 | Marriage before birth | Make sure that an individual's marriage date is >= their birth date
US16 | Divorce before marriage | Make sure that an individual's divorce date is >= their marriage date
US17 | Death before giving birth | child birth date is > parent death date + one year
US18 | Monogamy | An individual can have at most one spouse
US19 | Illegal spouse | An individual can't marry to their sibling unless they are not biologically related
US20 | Illegal marrige age | A man can't get married until 20, a woman can't get married until 18
US21
US22
US23
US24
US25
US26
US27

## Tests
AT ID | Story ID | Story Name | Input | Expected Output | Status
AT01 | US01 | Death before birth | Individual I01 (Groucho Marx) has birth date 01 JAN 2015 and death date 01 JAN 2014 | Error message "Individual I01 (Groucho Marx) has death date (01 JAN 2014) before birth date (01 JAN 2015)" | Passed
AT02 | US01 | Death before birth | Individual I02 (Harpo Marx) has birth date 01 JAN 1950 and death date 01 JAN 2015 | No error message | Passed
AT03 | US02 | Death before marriage | Individual I01 (Groucho Marx) has marriage date 01 JAN 2015 and death date 01 JAN 2014 | Error message "Individual I01 (Groucho Marx) has death date (01 JAN 2014) before marriage date (01 JAN 2015)" | Failed
AT04 | US02 | Death before marriage | Individual I02 (Harpo Marx) has marriage date 01 JAN 1980 and death date 01 JAN 2015 | No error message | Passed
AT05 | US03 | Marriage before birth | Individual I03 Chico Marx) has birth date 01 JAN 2015 and marriage date 01 JAN 2014 | Error message "Individual I03 (Chico Marx) has marriage date (01 JAN 2014) before birth date (01 JAN 2015)" | No data
AT06 | US03 | Marriage before birth | Individual I02 (Harpo Marx) has birth date 01 JAN 1950 and marriage date 01 JAN 1980 | No error message | Passed

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2014-09-22 | 36 |  | 0
2014-10-05 | 30 | 6 | 250 | 120 | 125
2014-10-19 | 24 | 6 | 400 | 90 | 100
2014-11-02 | 12 | 12 | 800 | 150 | 160
2014-11-16 | 6 | 6 | 900 | 80 | 75
2014-11-30 | 0 | 6 | 1000 | 60 | 100

## Sprint1
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Death before birth | AT01, AT02 | hm | Done | 150 | 60 | 120 | 90 | 2014-09-24
T01.01 | Store birth date |  | hm
T01.02 | Store death date |  | hm
T01.03 | Compare birth and death dates |  | hm
US02 | Death before marriage | AT03, AT04 | gh | Coding | 200 | 120
T02.01 | Find marriage record for individual |  | gh(at) | Done
T02.02 | Find marriage date |  | gh
T02.03 | Compare marriage date to birth date |  | gh(hm)
Review Results
Keep doing:
Meet twice a week
Text everyone when you discover a problem
Avoid:
Forgetting to commit changes to GitHub

## Sprint2
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint3
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint4
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint5
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed