## Team
Initials | First | Last | Email | GitHub Username
yw | Yanjun | Wu | ywu29@stevens.edu | LSYanJun
gc | Gong | Cheng | gcheng2@stevens.edu | chenggongtc
abg | Amog | bheemanakolli gurumallappa | abheeman@stevens.edu | amoghagurumallappa
|  |  | GitHub Repository: | SSW555tm052015s

## Backlog
Sprint | Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Added
1 | US01 | Inexistent ID | AT01~AT07 | gc | Done | 150 | 60 | 101 | 60 | 2015-02-27 | 2015-02-25
1 | US02 | Unmatched pointers | AT08~AT14 | gc | Done | 50 | 40 | 90 | 45 | 2015-02-28 | 2015-02-25
1 | US03 | Invalid date | AT15~AT21 | YW | Done | 80 | 45 | 162 | 60 | 2015-03-01 | 2015-02-25
1 | US04 | Invalid family members | AT24~AT26 | abg | Done | 80 | 45 | 44 | 45 | 2015-02-28 | 2015-02-25
1 | US05 | Death before birth | AT22~AT23 | YW | Done | 20 | 30 | 30 | 30 | 2015-03-01 | 2015-02-25
1 | US06 | Invalid gender | AT27~AT28 | abg | Done | 50 | 25 | 27 | 20 | 2015-03-01 | 2015-02-25
2 | US07 | Invalid age of an individual |  | gc | Done | 20 | 10 | 21 | 30 | 2015-03-07 | 2015-02-25
2 | US08 | Multiple roles in a family |  | gc | Done | 50 | 30 | 72 | 30 | 2015-03-07 | 2015-02-25
2 | US09 | Invalid ages in a family |  | YW | Done | 50 | 45 | 42 | 15 | 2015-03-09 | 2015-02-25
2 | US10 | Death before marriage |  | YW | Done | 30 | 10 | 31 | 20 | 2015-03-09 | 2015-02-25
2 | US11 | Marriage before birth |  |  |  | 30 | 10 |  |  |  | 2015-02-25
2 | US12 | Divorce before marriage |  |  |  | 30 | 10 |  |  |  | 2015-02-25
| US13 | Death before giving birth | [8 empty] | 2015-02-25
| US14 | Polygamy | [8 empty] | 2015-02-25
| US15 | Illegal spouse | [8 empty] | 2015-02-25
| US16 | Illegal marrige age | [8 empty] | 2015-02-25
| US17 | Amount of family members | [8 empty] | 2015-02-25
| US18 | Age gap among the children | [8 empty] | 2015-02-25
| US19 | Pregnancy limit | [8 empty] | 2015-02-25
| US20 | Child in family | [8 empty] | 2015-02-25
| US21 | Family rule | [8 empty] | 2015-02-25
| US22 | Completed information | [8 empty] | 2015-03-01
| US23 | Divorce before giving birth | [8 empty] | 2015-03-01
| US24 | Unique information | [8 empty] | 2015-03-01
| US25 | Last name rule | [8 empty] | 2015-03-09
| US26 | Birth date limitation | [8 empty] | 2015-03-09
| US27 | Multiple births rule | [8 empty] | 2015-03-09
| US28 | May-December marrige | [8 empty] | 2015-03-09
| US29 | Given birth before marriage | [8 empty] | 2015-03-09
| US30 | Marriage rule | [8 empty] | 2015-03-09

## Stories
Story ID | Story Name | Story Description | Acc Tests | Est Size | Est Time
US01 | Inexistent ID | Make sure that the ID of an individual in a family or the ID of a family of an individual exists | AT01~AT07 | 150 | 60
US02 | Unmatched pointers | Make sure that the pointers of an individual matches the pointers of the related families, and vice versa | AT08~AT14 | 50 | 40
US03 | Invalid date | Make sure that all the dates are before today | AT15~AT21 | 80 | 45
US04 | Invalid family members | A family must contain a husband and a wife | AT24~A26 | 20 | 30
US05 | Death before birth | Make sure that an individual's death date is >= their birth date | AT22~AT23 | 80 | 45
US06 | Invalid gender | Make sure that in a family, father is a male and mother is a female | AT27~AT28 | 50 | 25
US07 | Invalid age of an individual | Make sure that an individual's age is between 0 and 150 | AT29~AT31 | 20 | 10
US08 | Multiple roles in a family | Make sure an individual can play only one role in a family | AT32~AT33 | 50 | 30
US09 | Invalid ages in a family | Make sure that the parents are older than children in one family |  | 50 | 45
US10 | Death before marriage | Make sure that an individual's death date is >= their marriage date |  | 30 | 10
US11 | Marriage before birth | Make sure that an individual's marriage date is >= their birth date |  | 30 | 10
US12 | Divorce before marriage | Make sure that an individual's divorce date is >= their marriage date |  | 30 | 10
US13 | Death before giving birth | Make sure that in a family, mother's death date is >= her children's birth dates and father's death date + 10 months is >= his children's birth dates |  | 70 | 30
US14 | Polygamy | An individual can have at most one spouse |  | 50 | 20
US15 | Illegal spouse | An individual can't marry to their sibling |  | 100 | 45
US16 | Illegal marriage age | A man can't get married until 20, a woman can't get married until 18 |  | 30 | 10
US17 | Amount of family members | A family can have at most 8 members |  | 20 | 10
US18 | Age gap among the children | There should be at least 1 year age difference unless they were born on the same day |  | 50 | 20
US19 | Pregnancy limit | Wife can give birth between the age of 18 and 50
US20 | Child in family | A person could be a child of only one family
US21 | Family rule | A person should be linked to at least one family
US22 | Completed information | Every person must have completed information(name, sex, birthday) and every family must have completed information(marriage date)
US23 | Divorce before giving birth | If the parents were divorced in a family, make sure that all the children were born before the divorce date
US24 | Unique information | An individual can only have one tag of sex, name, birthdate, etc.
US25 | Last name rule | The children should have the same last name as their father
US26 | Birth date limitation | All the individuals should be born after the year of 1900. We do not record ancient people
US27 | Multiple births rule | There should be no more than 4 children that are born on the same day
US28 | May-December marriage | The age difference between two spouses should be less than 30 years
US29 | Given birth before marriage | Children should be born after their parents' marriage
US30 | Marriage rule | Children's marriage should after parents' marriage

## Tests
AT ID | Story ID | Story Name | Input | Expected Output | Status
AT01 | US01 | Inexistent ID | Individual I1(Jacky /Mao/) is the child of F22 | Error message " Individual I1(Jacky /Mao/) is a child of an inexistent Family F22." | Passed
AT02 | US01 | Inexistent ID | Individual I3(Katie /Brown/) is the spouse of Family F23 | Error message " Individual I3(Katie /Brown/) is a spouse of an inexistent Family F23." | Passed
AT03 | US01 | Inexistent ID | Family F1's husband is Individual I18 | Error message " Family F1 has a husband who is an inexistent Individual I18." | Passed
AT04 | US01 | Inexistent ID | Family F2 has a child who is Individual I15 | Error message " Family F2 has a child who is an inexistent Individual I15." | Passed
AT05 | US01 | Inexistent ID | Family F3's wife is Individual I31 | Error message " Family F3 has a wife who is an inexistent Individual I31." | Passed
AT06 | US01 | Inexistent ID | Individual I5(Emily /Mao/) is the child of F2 and the spouse of F5 | No error message | Passed
AT07 | US01 | Inexistent ID | Family F4's husband is Individual I8(Kevin /Brown/), wife is Individual I9(Elena /Wilson/) and child is Individual I3(Katie /Brown/) | No error message | Passed
AT08 | US02 | Unmatched pointers | Individual I1(Jacky /Mao/) is one of the spouse of Family F1, and Family F1's husband is Individual I18 and wife is Individual I12 | Error message " Individual I1(Jacky /Mao/) is a spouse of Family F1, but Family F1 does not have the spouse of I1(Jacky /Mao/)." | Passed
AT09 | US02 | Unmatched pointers | Individual I3(Katie /Brown/) is one of the spouse of Family F3, and Family F3's husband is Individual I4 and wife is Individual I31 | Error message " Individual I3(Katie /Brown/) is a spouse of Family F3, but Family F3 does not have the spouse of I3(Katie /Brown/)." | Passed
AT10 | US02 | Unmatched pointers | Individual I5(Emily /Mao/) is one of the child of Family F2, and Family F2's children are I1 and I15 | Error message " Individual I5(Emily /Mao/) is a child of Family F2, but Family F2 does not have the child of I5(Emily /Mao/)." | Passed
AT11 | US02 | Unmatched pointers | Family F2's wife is Individual I3(Katie /Brown/), I3(Katie /Brown/) is the spouse of F23 and F3 | Error message " Family F2's wife is Individual I3(Katie /Brown/), but Individual I3(Katie /Brown/) is not the wife of Family F2." | Passed
AT12 | US02 | Unmatched pointers | Family F2 has a child who is Individual I1(Jacky /Mao/), and I1(Jacky /Mao/) is the child of F22 | Error message " Family F2 has a child who is Individual I1(Jacky /Mao/), but Individual I1(Jacky /Mao/) is not a child of Family F2." | Passed
AT13 | US02 | Unmatched pointers | Individual I2(Jianguo /Mao/) is one of the spouse of Family F2, and Family F2's husband is Individual I2(Jianguo /Mao/) | No error message | Passed
AT14 | US02 | Unmatched pointers | Family F3's husband is Individual I4(Edwin /Moore/), and Individual I4(Edwin /Moore/) is one of the spouse of Family F3 | No error message | Passed
AT15 | US03 | Invalid date | Individual I13(Bob /Shaw/)'s death date is 29 FEB 1999 | Individual I13(Bob /Shaw/) has an invalid death date.(29 FEB 1999) Death date doesn't exist. | Passed
AT16 | US03 | Invalid date | Individual I9(Elena /Wilson/)'s birthday is 1 JAN 2016, which is not possible known | Individual I9(Elena /Wilson/) has an invalid birth date.(1 JAN 2016) Birthday before current date. | Passed
AT17 | US03 | Invalid date | Individual I13(Bob /Shaw/)'s birth date is 31 JUN 1938 | Individual I13(Bob /Shaw/) has an invalid birth date.(31 JUN 1938) Birthday doesn't exist. | Passed
AT18 | US03 | Invalid date | Individual I11(James /Brown/)'s death date is 29 Feb 2400 | Individual I11(James /Brown/) has an invalid death date.(29 FEB 2400)Death date before current date. | Passed
AT19 | US03 | Invalid date | Individual I10(Jen /Brown/) was born 29 FEB 2000 | No error message | Passed
AT20 | US03 | Invalid date | Family F1 marriage date is 2 FEB 2018 | Family F1 has an invalid marriage date (2 Feb 2018). Marriage date beforen current date. | Passed
AT21 | US03 | Invalid date | Family F3 marriage date is 31 NOV 1987 | Family F3 has an invalid divorce date(31 NOV 1987). Divorce date doesn't exist. | Passed
AT22 | US05 | Death before birth | Individual I10(Jen /Brown/) was born 29 FEB 2000 and died on 20 May 1935 | Individual I10(Jen /Brown/) death before birth.Birth: 29 FEB 2000 Death: 20 MAY 1935 | Passed
AT23 | US05 | Death before birth | Individual I5(Emily /Mao/) was born on 11 SEP 1993 and died on 31 OCT 2014 | No error message | Passed
AT24 | US04 | Invalid family members | Family F1 doesn't have information of a husband | Family F1 does not have a husband. | Passed
AT25 | US04 | Invalid family members | Family F3 doesn't have information of a wife | Family F3 does not have a wife. | Passed
AT26 | US04 | Invalid family members | Family F2 has 2 husbands: I2 and I4 | Family F2 has 2 husbands: I2(Jianguo /Mao/), I4(Edwin /Moore/). | Passed
AT27 | US06 | Invalid gender | Individual I3 of family F2 is a male | Famil F2's wife I3(Katie /Brown/) is not FEMALE. | Passed
AT28 | US06 | Invalid gender | Individual I8 of family F4 is a female | Famil F4's husdband I8(Kevin /Brown/) is not MALE. | Passed
AT29 | US07 | Invalid age of an individual | Individual I1(Jacky /Mao/)'s birth date is 27 JAN 1848, and he is not dead. | Individual I1(Jacky /Mao/) is older than 150 years old. Birth date(27 JAN 1848), not dead. | Passed
AT30 | US07 | Invalid age of an individual | Individual I8(Kevin /Brown/)'s birth date is 1 NOV 1848, and death date is 11 SEP 2001. | Individual I8(Kevin /Brown/) was older than 150 years old. Birth date(1 NOV 1848), deat date(11 SEP 2001). | Passed
AT31 | US07 | Invalid age of an individual | Individual I6(Lisabella /Taylor/)'s birth date is 6 JUN 2014, she is not dead. | No error message | Passed
AT32 | US08 | Multiple roles in a family | Individual I3(Katie /Brown/) is the wife and the child of Family F2. | Individual I3(Katie /Brown/) plays multiple roles in Family F2: child, wife | Passed
AT33 | US08 | Multiple roles in a family | Individual I2(Jianguo /Mao/) is the husband of Family F2. | No error message | Passed
AT34
AT35
AT36
AT37
AT38
AT39
AT40
AT41
AT42
AT43
AT44
AT45
AT46
AT47
AT48
AT49
AT50
AT51
AT52
AT53
AT54
AT55
AT56
AT57
AT58
AT59
AT60
AT61
Note on E22: Yanjun:

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2015-02-25 | 25 |  | 598
2015-03-01 | 19 | 6 | 1034 | 260 | 100.6154

## Sprint1
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Inexistent ID | AT01~AT07 | gc | Done | 150 | 60 | 98 | 60 | 2015-02-27
T01.01 | Check the existance of family IDs of every individual |  | gc
T01.02 | Link the existant family IDs to the related families |  | gc
T01.03 | Check the existance of individual IDs of every family |  | gc
T01.04 | Link the existant individual IDs to the related individuals |  | gc
US02 | Unmatched pointers | AT08~AT14 | gc | Done | 50 | 40 | 72 | 45 | 2015-02-28
T02.01 | Check if the family pointers of an individual point back to the individual(as the same role in the family) |  | gc
T02.02 | Check if the individual pointers of a family point back to the family(as the same role in the family) |  | gc
US03 | Invalid date | AT15~AT21 | yw | Done | 80 | 45 | 162 | 60 | 2015-03-01
T03.01 | Get current date(year, month, day) |  | yw
T03.02 | Get every date from stored structure |  | yw
T03.03 | check if the event date exists |  | yw
T03.04 | check if the event date of individual or family is after current date |  | yw
US05 | Death before birth | AT22~AT23 | yw | Done | 20 | 30 | 30 | 30 | 2015-03-01
T05.01 | Get individual's birth date |  | yw
T05.02 | Get individual's death date |  | yw
T05.03 | Check if individual's death is before birth
US04 | Invalid family members | AT24~AT26 | abg | Done | 80 | 45 | 44 | 45 | 2015-02-28
T04.01 | Find all the husbands and wives in each family |  | abg
T04.02 | count the amount of husbands and wives respectively |  | abg
T04.03 | check the amount is less, equal or greater than one |  | abg
US06 | Invalid gender | AT27~AT28 | abg | Done | 50 | 25 | 27 | 20 | 2015-03-01
T06.01 | Get the sex of a husband and the sex of a wife in a family |  | abg
T06.02 | check if the husband is a male and the wife is a female |  | abg
Review Results
Keep doing:
Meet at least twice a week
Inform everyone when you discover a problem
Modify the user stories we are about to implement next sprint to more proper and completed
Add more user stories if you come up new one
Avoid:
Forgetting to commit changes to GitHub

## Sprint2
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US07 | Invalid age of an individual | AT29~AT31 | gc | Done | 20 | 10 | 21 | 30 | 2015-03-07
T07.01 | Get the birth date of the individual |  | gc
T07.02 | Get the death date of the individual(if exist) |  | gc
T07.03 | Check the age of the individual |  | gc
US08 | Multiple roles in a family | AT32~AT33 | gc | Done | 50 | 30 | 72 | 30 | 2015-03-07
T08.01 | Get all the individuals of the family |  | gc
T08.02 | Sort the individuals by ID |  | gc
T08.03 | Check if some individuals play multiple roles in the family |  | gc
US09 | Invalid ages in a family |  | YW | done | 50 | 45 | 42 | 15 | 2015-03-09
T09.01 | get access to each family record |  | YW
T09.02 | get each husband /wifebirth date |  | YW
T09.03 | get each child birth date |  | YW
T09.04 | compare husband/wife birth date with child birth date |  | YW
US10 | Death before marriage |  | YW |  | 30 | 10 | 31 | 20 | 2015-03-09
T10.01 | get access to each family record |  | YW
T10.02 | if there is no marriage date then continue to next family record |  | YW
T10.03 | get each husband/wife death date |  | YW
T10.04 | if there is no death date then continue |  | YW
T10.05 | compare the death date with marriage date |  | YW
US11 | Marriage before birth |  |  |  | 30 | 10
US12 | Divorce before marriage |  |  |  | 30 | 10

## Sprint3
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US13 | Death before giving birth |  | gc |  | 70 | 30
US14 | Polygamy |  | gc |  | 50 | 20
US15 | Illegal spouse |  | yw |  | 100 | 45
US16 | Illegal marrige age |  | yw |  | 30 | 10
US17 | Amount of family members |  | abg |  | 20 | 10
US18 | Age gap among the children |  | abg |  | 50 | 20

## Sprint4
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint5
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed