## Team
Initials | First | Last | Email | GitHub Username
yw | Yanjun | Wu | ywu29@stevens.edu | LSYanJun
gc | Gong | Cheng | gcheng2@stevens.edu | chenggongtc
abg | Amog | bheemanakolli gurumallappa | abheeman@stevens.edu | amoghagurumallappa
|  |  | GitHub Repository: | SSW555tm052015s

## Backlog
Sprint | Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Added
1 | US01 | Inexistent ID | AT01~AT07 | gc | Done | 150 | 60 | 101 | 60 | 2015-02-27 | 2015-02-25
1 | US02 | Unmatched pointers | AT08~AT14 | gc | Done | 50 | 40 | 90 | 45 | 2015-02-28 | 2015-02-25
1 | US03 | Invalid date | AT15~AT21 | YW | Done | 80 | 45 | 162 | 60 | 2015-03-01 | 2015-02-25
1 | US04 | Invalid family members | AT24~AT26 | abg | Done | 80 | 45 | 44 | 45 | 2015-02-28 | 2015-02-25
1 | US05 | Death before birth | AT22~AT23 | YW | Done | 20 | 30 | 30 | 30 | 2015-03-01 | 2015-02-25
1 | US06 | Invalid gender | AT27~AT28 | abg | Done | 50 | 25 | 27 | 20 | 2015-03-01 | 2015-02-25
2 | US07 | Invalid age of an individual | AT29~AT31 | gc | Done | 20 | 10 | 21 | 30 | 2015-03-07 | 2015-02-25
2 | US08 | Multiple roles in a family | AT32~AT33 | gc | Done | 50 | 30 | 72 | 30 | 2015-03-07 | 2015-02-25
2 | US09 | Invalid ages in a family | AT34~36 | YW | Done | 50 | 45 | 42 | 15 | 2015-03-09 | 2015-02-25
2 | US10 | Death before marriage | AT37~38 | YW | Done | 30 | 10 | 31 | 20 | 2015-03-09 | 2015-02-25
2 | US11 | Marriage before birth | AT39~41 | abg | done | 30 | 10 | 31 | 25 | 2015-03-11 | 2015-02-25
2 | US12 | Divorce before marriage | AT42~43 | abg | done | 30 | 10 | 15 | 10 | 2015-03-11 | 2015-02-25
3 | US13 | Death before giving birth | AT44~46 | gc | Done | 70 | 30 | 115 | 40 | 2015-03-24 | 2015-02-25
3 | US14 | Polygamy | AT47~48 | gc | Done | 50 | 20 | 45 | 30 | 2015-03-24 | 2015-02-25
3 | US15 | Illegal spouse | AT49~50 | YW | Done | 100 | 45 | 19 | 30 | 2015-03-27 | 2015-02-25
3 | US16 | Illegal marrige age | AT51~54 | YW | Done | 30 | 10 | 24 | 25 | 2015-03-27 | 2015-02-25
3 | US17 | Amount of family members | AT55~56 | abg | Done | 20 | 10 | 9 | 10 | 2015-03-29 | 2015-02-25
3 | US18 | Age gap among the children | AT57~58 | abg | Done | 50 | 20 | 34 | 25 | 2015-03-29 | 2015-02-25
| US19 | Pregnancy limit | AT73~74 | abg | Done | 50 | 25 | 30 | 25 | 2015-04-12 | 2015-02-25
| US20 | Child in family | AT59~60 | gc | Done | 75 | 30 | 15 | 30 | 2015-04-06 | 2015-02-25
| US21 | Family rule | AT77~78 | yw | done | 100 | 50 | 11 | 10 | 2015-04-12 | 2015-02-25
| US22 | Completed information | AT79~85 | yw | done | 70 | 35 | 30 | 20 | 2015-04-12 | 2015-03-01
| US23 | Divorce before giving birth | AT75~76 | abg | Done | 75 | 30 | 20 | 20 | 2015-04-12 | 2015-03-01
| US24 | Unique information | AT61~72 | gc | done | 100 | 45 | 226 | 90 | 2015-04-06 | 2015-03-01
| US25 | Last name rule | AT86~87 | gc | done | 30 | 35 | 31 | 30 | 2015-04-20 | 2015-03-09
| US26 | Birth date limitation | [8 empty] | 2015-03-09
| US27 | Multiple births rule | AT88~89 | gc | done | 35 | 70 | 43 | 50 | 2015-04-20 | 2015-03-09
| US28 | May-December marrige | [8 empty] | 2015-03-09
| US29 | Given birth before marriage | [8 empty] | 2015-03-09
| US30 | Marriage rule | [8 empty] | 2015-03-09

## Stories
Story ID | Story Name | Story Description | Acc Tests | Est Size | Est Time
US01 | Inexistent ID | Make sure that the ID of an individual in a family or the ID of a family of an individual exists | AT01~AT07 | 150 | 60
US02 | Unmatched pointers | Make sure that the pointers of an individual matches the pointers of the related families, and vice versa | AT08~AT14 | 50 | 40
US03 | Invalid date | Make sure that all the dates are before today | AT15~AT21 | 80 | 45
US04 | Invalid family members | A family must contain a husband and a wife | AT24~A26 | 20 | 30
US05 | Death before birth | Make sure that an individual's death date is >= their birth date | AT22~AT23 | 80 | 45
US06 | Invalid gender | Make sure that in a family, father is a male and mother is a female | AT27~AT28 | 50 | 25
US07 | Invalid age of an individual | Make sure that an individual's age is between 0 and 150 | AT29~AT31 | 20 | 10
US08 | Multiple roles in a family | Make sure an individual can play only one role in a family | AT32~AT33 | 50 | 30
US09 | Invalid ages in a family | Make sure that the parents are older than children in one family | AT34~36 | 50 | 45
US10 | Death before marriage | Make sure that an individual's death date is >= their marriage date | AT37~38 | 30 | 10
US11 | Marriage before birth | Make sure that an individual's marriage date is >= their birth date | AT39~41 | 30 | 10
US12 | Divorce before marriage | Make sure that an individual's divorce date is >= their marriage date | AT42~43 | 30 | 10
US13 | Death before giving birth | Make sure that in a family, mother's death date is >= her children's birth dates and father's death date + 10 months is >= his children's birth dates | AT44~46 | 70 | 30
US14 | Polygamy | An individual can have at most one spouse currently | AT47~48 | 50 | 20
US15 | Illegal spouse | An individual can't marry to their sibling | AT49~50 | 100 | 45
US16 | Illegal marriage age | A man can't get married until 20, a woman can't get married until 18 | AT51~54 | 30 | 10
US17 | Amount of family members | A family can have at most 8 members | AT55~56 | 20 | 10
US18 | Age gap among the children | There should be at least 1 year age difference unless they were born on the same day | AT57~58 | 50 | 20
US19 | Pregnancy limit | Wife can give birth between the age of 18 and 50 | AT73~74 | 50 | 25
US20 | Child in family | A person could be a child of only one family | AT59~60 | 75 | 30
US21 | Family rule | A person should be linked to at least one family | AT77~78 | 100 | 50
US22 | Completed information | Every person must have completed information(name, sex, birthday) and every family must have completed information(marriage date) | AT79~85 | 70 | 35
US23 | Divorce before giving birth | If the parents were divorced in a family, make sure that all the children were born before the divorce date | AT75~76 | 75 | 30
US24 | Unique information | An individual should only have one tag of sex, name, birthdate, and at most one tag of death date; a family should only have one tag of marriage date and at most one tag of divorce date. | AT61~72 | 100 | 45
US25 | Last name rule | The children should have the same last name as their father | AT86~87 | 30 | 35
US26 | Birth date limitation | All the individuals should be born after the year of 1900. We do not record ancient people |  | 15 | 30
US27 | Multiple births rule | There should be no more than 4 children that are born on the same day in one family | AT88~89 | 35 | 70
US28 | May-December marriage | The age difference between two spouses should be less than 30 years |  | 20 | 15
US29 | Given birth before marriage | Children should be born after their parents' marriage |  | 35 | 40
US30 | Marriage rule | Children's marriage should after parents' marriage |  | 30 | 35

## Tests
AT ID | Story ID | Story Name | Input | Expected Output | Status
AT01 | US01 | Inexistent ID | Individual I1(Jacky /Mao/) is the child of F22 | Error message " Individual I1(Jacky /Mao/) is a child of an inexistent Family F22." | Passed
AT02 | US01 | Inexistent ID | Individual I3(Katie /Brown/) is the spouse of Family F23 | Error message " Individual I3(Katie /Brown/) is a spouse of an inexistent Family F23." | Passed
AT03 | US01 | Inexistent ID | Family F1's husband is Individual I18 | Error message " Family F1 has a husband who is an inexistent Individual I18." | Passed
AT04 | US01 | Inexistent ID | Family F2 has a child who is Individual I15 | Error message " Family F2 has a child who is an inexistent Individual I15." | Passed
AT05 | US01 | Inexistent ID | Family F3's wife is Individual I31 | Error message " Family F3 has a wife who is an inexistent Individual I31." | Passed
AT06 | US01 | Inexistent ID | Individual I5(Emily /Mao/) is the child of F2 and the spouse of F5 | No error message | Passed
AT07 | US01 | Inexistent ID | Family F4's husband is Individual I8(Kevin /Brown/), wife is Individual I9(Elena /Wilson/) and child is Individual I3(Katie /Brown/) | No error message | Passed
AT08 | US02 | Unmatched pointers | Individual I1(Jacky /Mao/) is one of the spouse of Family F1, and Family F1's husband is Individual I18 and wife is Individual I12 | Error message " Individual I1(Jacky /Mao/) is a spouse of Family F1, but Family F1 does not have the spouse of I1(Jacky /Mao/)." | Passed
AT09 | US02 | Unmatched pointers | Individual I3(Katie /Brown/) is one of the spouse of Family F3, and Family F3's husband is Individual I4 and wife is Individual I31 | Error message " Individual I3(Katie /Brown/) is a spouse of Family F3, but Family F3 does not have the spouse of I3(Katie /Brown/)." | Passed
AT10 | US02 | Unmatched pointers | Individual I5(Emily /Mao/) is one of the child of Family F2, and Family F2's children are I1 and I15 | Error message " Individual I5(Emily /Mao/) is a child of Family F2, but Family F2 does not have the child of I5(Emily /Mao/)." | Passed
AT11 | US02 | Unmatched pointers | Family F2's wife is Individual I3(Katie /Brown/), I3(Katie /Brown/) is the spouse of F23 and F3 | Error message " Family F2's wife is Individual I3(Katie /Brown/), but Individual I3(Katie /Brown/) is not the wife of Family F2." | Passed
AT12 | US02 | Unmatched pointers | Family F2 has a child who is Individual I1(Jacky /Mao/), and I1(Jacky /Mao/) is the child of F22 | Error message " Family F2 has a child who is Individual I1(Jacky /Mao/), but Individual I1(Jacky /Mao/) is not a child of Family F2." | Passed
AT13 | US02 | Unmatched pointers | Individual I2(Jianguo /Mao/) is one of the spouse of Family F2, and Family F2's husband is Individual I2(Jianguo /Mao/) | No error message | Passed
AT14 | US02 | Unmatched pointers | Family F3's husband is Individual I4(Edwin /Moore/), and Individual I4(Edwin /Moore/) is one of the spouse of Family F3 | No error message | Passed
AT15 | US03 | Invalid date | Individual I13(Bob /Shaw/)'s death date is 29 FEB 1999 | Individual I13(Bob /Shaw/) has an invalid death date.(29 FEB 1999) Death date doesn't exist. | Passed
AT16 | US03 | Invalid date | Individual I9(Elena /Wilson/)'s birthday is 1 JAN 2016, which is not possible known | Individual I9(Elena /Wilson/) has an invalid birth date.(1 JAN 2016) Birthday before current date. | Passed
AT17 | US03 | Invalid date | Individual I13(Bob /Shaw/)'s birth date is 31 JUN 1938 | Individual I13(Bob /Shaw/) has an invalid birth date.(31 JUN 1938) Birthday doesn't exist. | Passed
AT18 | US03 | Invalid date | Individual I11(James /Brown/)'s death date is 29 Feb 2400 | Individual I11(James /Brown/) has an invalid death date.(29 FEB 2400)Death date before current date. | Passed
AT19 | US03 | Invalid date | Individual I10(Jen /Brown/) was born 29 FEB 2000 | No error message | Passed
AT20 | US03 | Invalid date | Family F1 marriage date is 2 FEB 2018 | Family F1 has an invalid marriage date (2 Feb 2018). Marriage date beforen current date. | Passed
AT21 | US03 | Invalid date | Family F3 marriage date is 31 NOV 1987 | Family F3 has an invalid divorce date(31 NOV 1987). Divorce date doesn't exist. | Passed
AT22 | US05 | Death before birth | Individual I10(Jen /Brown/) was born 29 FEB 2000 and died on 20 May 1935 | Individual I10(Jen /Brown/) death before birth.Birth: 29 FEB 2000 Death: 20 MAY 1935 | Passed
AT23 | US05 | Death before birth | Individual I5(Emily /Mao/) was born on 11 SEP 1993 and died on 31 OCT 2014 | No error message | Passed
AT24 | US04 | Invalid family members | Family F1 doesn't have information of a husband | Family F1 does not have a husband. | Passed
AT25 | US04 | Invalid family members | Family F3 doesn't have information of a wife | Family F3 does not have a wife. | Passed
AT26 | US04 | Invalid family members | Family F2 has 2 husbands: I2 and I4 | Family F2 has 2 husbands: I2(Jianguo /Mao/), I4(Edwin /Moore/). | Passed
AT27 | US06 | Invalid gender | Individual I3 of family F2 is a male | Famil F2's wife I3(Katie /Brown/) is not FEMALE. | Passed
AT28 | US06 | Invalid gender | Individual I8 of family F4 is a female | Famil F4's husdband I8(Kevin /Brown/) is not MALE. | Passed
AT29 | US07 | Invalid age of an individual | Individual I1(Jacky /Mao/)'s birth date is 27 JAN 1848, and he is not dead. | Individual I1(Jacky /Mao/) is older than 150 years old. Birth date(27 JAN 1848), not dead. | Passed
AT30 | US07 | Invalid age of an individual | Individual I12(Grace /Li/)'s birth date is 21 APR 1839, and death date is 21 APR 1990. | Individual I12(Grace /Li/) was older than 150 years old. Birth date(21 APR 1839), deat date(21 APR 1990). | Passed
AT31 | US07 | Invalid age of an individual | Individual I6(Lisabella /Taylor/)'s birth date is 6 JUN 2014, she is not dead. | No error message | Passed
AT32 | US08 | Multiple roles in a family | Individual I3(Katie /Brown/) is the wife and the child of Family F2. | Individual I3(Katie /Brown/) plays multiple roles in Family F2: child, wife | Passed
AT33 | US08 | Multiple roles in a family | Individual I2(Jianguo /Mao/) is the husband of Family F2. | No error message | Passed
AT34 | US09 | Invalid ages in a family | In family F2, wife I3 was born 14 FEB 1965, and child I5 was born 11 SEP 1993 | No error message | Passed
AT35 | US09 | Invalid ages in a family | In family F4, husband I8 was born 14 FEB 1965 as same as child I3 was born 14 FEB 1965 | Husband I8(Kevin /Brown/) of family F4(14 FEB 1965) is not older than the child I3(Katie /Brown/)(14 FEB 1965) | Passed
AT36 | US09 | Invalid ages in a family | In family F6, husband I8 was born(14 FEB 1965) after child I11(1 MAY 1962) | Husband I8(Kevin /Brown/) of family F6(14 FEB 1965) is not older than the child I11(James /Brown/)(1 MAY 1962) | Passed
AT37 | US10 | Death before marriage | In family F3, Marriage date is 1 Jan 1985, wife I3 was died on 8 AUG 1980 which is before marriage | Family F3, wife I3(Katie /Brown/) death (8 AUG 1980) before marriage (1 JAN 1985) | Passed
AT38 | US10 | Death before marriage | In family F6, marriage date is 1 JAN 1985, husband I8 died on (11 SEP 2001) | No error message | Passed
AT39 | US11 | Marriage before birth | In family F1, marriage date is 1 JAN 1985,husband I1 was born on 1 JAN 1840 and 27 JAN 1848 | Individual I1(Jacky /Mao/)'s marrige(1 JAN 1840) before birth(27 JAN 1848). | passed
AT40 | US11 | Marriage before birth | In family F5, marriage date is 1 JAN 1992,Wife I5 birth date is 11 SEP 1993 | Individual I5(Emily /Mao/)'s marrige(1 JAN 1992) before birth(11 SEP 1993). | Passed
AT41 | US11 | Marriage before birth | In family F3, Marriage date is 1 Jan 1985, Husband I4 and Wife I3 was born on 1 OCT 1960 and 14 Feb 1965 | No error message | Passed
AT42 | US12 | Divorce before marriage | In Family F3, Mariage date is 1 JAN 1985,Divorce date is 31 DEC 1949 | Family F3's divorce date(31 DEC 1949) before marrige date(1 JAN 1985). | Passed
AT43 | US12 | Divorce before marriage | In family F6, marriage date is 1 JAN 1985, Divorce date is 31 DEC 1987 | No error message | Passed
AT44 | US13 | Death before giving birth | In Family F5, wife I5(Emily /Mao/) died on 5 JUN 2014, and child I6(Lisabella /Taylor/) was born on 6 JUN 2014 | In Family F5, wife I5(Emily /Mao/)'s death date(5 JUN 2014) is < her child I6(Lisabella /Taylor/)'s birth date(6 JUN 2014) | Passed
AT45 | US13 | Death before giving birth | In Family F5, husband I7(Chris /Taylor/) died on 6 JUN 2013, and child I6(Lisabella /Taylor/) was born on 6 JUN 2014 | In Family F5, husband I7(Chris /Taylor/)'s death date(6 JUN 2013) + 10 months is < his child I6(Lisabella /Taylor/)'s birth date(6 JUN 2014) | Passed
AT46 | US13 | Death before giving birth | In Family F6, husband I8(Kevin /Brown/) died on 11 SEP 2001, wife I10(Jen /Brown/) not dead, child I11(James /Brown/) was born on 1 MAY 1962 | No error message | Passed
AT47 | US14 | Polygamy | Individual I8(Kevin /Brown/) is the husband of Family F4 and Family F6 currently | Individual I8(Kevin /Brown/) has more than one spouse currently: I9(Elena /Wilson/) in Family F4, I10(Jen /Brown/) in Family F6. | Passed
AT48 | US14 | Polygamy | Individual I10(Jen /Brown/) is the wife of Family F6 only | No error message | Passed
AT49 | US15 | Illegal spouse | Individual I3(Katie /Brown/) and I4(Edwin /Moore/) are siblings but they get married | Individual I3(Katie /Brown/) and Individual I4(Edwin /Moore/) are siblings in family F4 but they get married in family F3 | Passed
AT50 | US15 | Illegal spouse | In family F2, individual I2 and I3 get married legally. | No error message | Passed
AT51 | US16 | Illegal marriage age | Individual I1 was born on 27 Jan 1970 and got married on 1 Jan 1985 | Individual I1(Jacky /Mao/)'s birthday is 27 JAN 1970 and he got married when he was uder 20. Marriage date is 1 JAN 1985. | Passed
AT52 | US16 | Illegal marriage age | Individual I12 was born on 21 Apr 1970 and got married on 1 Jan 1985 | Individual I12(Grace /Li/)'s birthday is 21 APR 1970 and she got married when she was uder 18. Marriage date is 1 JAN 1985. | Passed
AT53 | US16 | Illegal marriage age | Individual I7 was born on 11 Nov 1970 and got married on 1 Jan 1985 | Individual I7(Chris /Taylor/)'s birthday is 11 NOV 1970 and he got married when he was uder 20. Marriage date is 1 JAN 1985. | Passed
AT54 | US16 | Illegal marriage age | Individual I5 was born on 11 Sep 1970 and got married on 1 Jan 1985 | Individual I5(Emily /Mao/)'s birthday is 11 SEP 1970 and she got married when she was uder 18. Marriage date is 1 JAN 1985. | Passed
AT55 | US17 | Amount of family members | Individual I2 and I3 have 7 children | Family F2 has more than 8 members (9). | Passed
AT56 | US17 | Amount of family members | Individual I8 and I9 have two children | No error message | Passed
AT57 | US18 | Age gap among the children | Individual I5 was born on 11 SEP 1970 and Individual I1 born on 27 JAN 1970 | In Family F2, child I5(Emily /Mao/) and child I1(Jacky /Mao/) are not multiple births but born within one year. | Passed
AT58 | US18 | Age gap among the children | Individual I3 was born on 14 FEB 1965 and Individual I4 born on 1 OCT 1960 | No error message | Passed
AT59 | US20 | Child in family | Individual I1 is the child of both Family F2 and Family F3 | Individual I1(Jacky /Mao/) is the child of multiple families: Family F2, Family F3. | Passed
AT60 | US20 | Child in family | Individual I3 is the child of only Family F4 | No error message | Passed
AT61 | US24 | Unique information | Individual I1 has two names: Jacky /Mao/ and Jackie /Mao/ | Individual I1 has more than one name tag: Jacky /Mao/, Jackie /Mao/. | Passed
AT62 | US24 | Unique information | Individual I1 has two sexes: F, M | Individual I1 has more than one sex tag: F, M. | Passed
AT63 | US24 | Unique information | Individual I1 has two birthdays: 27 JAN 1960 and 27 JAN 1970 | Individual I1 has more than one birthday tag: 27 JAN 1960, 27 JAN 1970. | Passed
AT64 | US24 | Unique information | Individual I1 has two death dates: 1 JAN 2014 and 1 FEB 2014 | Individual I1 has more than one death date tag: 1 JAN 2014, 1 FEB 2014. | Passed
AT65 | US24 | Unique information | Individual I2 does not have a name | Individual I2 does not have a name tag. | Passed
AT66 | US24 | Unique information | Individual I2 does not have a sex | Individual I2 does not have a sex tag. | Passed
AT67 | US24 | Unique information | Individual I2 does not have a birthday | Individual I2 does not have a birthday tag. | Passed
AT68 | US24 | Unique information | Individual I3 has one name, one sex, one birthday and zero death date | No error message | Passed
AT69 | US24 | Unique information | Family F4 does not have a marriage date | Family F4 does not have a marriage date tag. | Passed
AT70 | US24 | Unique information | Family F5 has two marriage date: 2 JAN 2000 and 1 JAN 2000 | Family F5 has more than one marriage date tag: 2 JAN 2000, 1 JAN 2000. | Passed
AT71 | US24 | Unique information | Family F5 has two divorce date: 5 JAN 2014 and 5 JAN 2014 | Family F5 has more than one divorce date tag: 5 JAN 2014, 5 JAN 2014. | Passed
AT72 | US24 | Unique information | Family F6 has one marriage date and zero divorce date | No error message | Passed
AT73 | US19 | Pregnancy limit | In Family F4, wife I9(Elena /Wilson/) was born on 1 NOV 1941 while child I3(Katie /Brown/) was born on 14 FEB 1950 | In Family F4, wife I9(Elena /Wilson/) gave birth to child I3(Katie /Brown/) when she was 9(not between 18 and 50) | Passed
AT74 | US19 | Pregnancy limit | Individaul I9 is in pregnency age, Her birth date is 1991 | No error message | Passed
AT75 | US23 | Divorce before giving birth | In family F3, Divorce date is 31 DEC 1972, Child birth date is 27 JAN 1974, born after Divorce | Family F3 divorce Date is(31 DEC 1972) and child's birth Date is (27 JAN 1974). | Passed
AT76 | US23 | Divorce before giving birth | In Family F5, Divorce date is 5 JAN 2014, Child birth date is 6 JUN 2011, Born before divorce | No error message | Passed
AT77 | US21 | Family rule | Individual I11(James /Brown/) doesn't have a fams nor a famc record | Individual I11 (James /Brown/) doesn't belong to any family. | Passed
AT78 | US21 | Family rule | Individual I12(Grace /Li/) is a wife in family F1, she has a fams record | No error message | Passed
AT79 | US22 | Completed information | Individual I2 doesn't have a name tag nor a name | Individual I2 doesn't complete information(missing name). | Passed
AT80 | US22 | Completed information | Individual I6 has a name tag but doesn't have a name record | Individual I6 doesn't complete information(missing name). | Passed
AT81 | US22 | Completed information | Individual I7 has a sex tag but doesn't have a gender record | Individual I7 (Chris /Taylor/) doesn't complete information(missing gender). | Passed
AT82 | US22 | Completed information | Individual I8 has a birt tag but doesn't have a birthday record | Individual I8 (Kevin /Brown/) doesn't complete information(missing birth date). | Passed
AT83 | US22 | Completed information | Individual I9 complete the information of name, sex and birthday | No error message | Passed
AT84 | US22 | Completed information | family F4 has a marr tag but doesn't have a marriage date record | Family F4 doesn't complete information(missing marriage date). | Passed
AT85 | US22 | Completed information | family F1 complete the information of marriage date | No error message | Passed
AT86 | US25 | Last name rule | In Family F2, husband I2's last name is Mao, while child I1's last name is Gao | In Family F2, husband I2(Jianguo /Mao/) and child I1(Jacky /Gao/) don't have the same last name. | Passed
AT87 | US25 | Last name rule | In Family F2, husband I2's last name is Mao, and child I5's last name is Mao | No error message | Passed
AT88 | US27 | Multiple births rule | In Family F2, child I5, I14, I15, I16 and I17 were all born on 11 SEP 1971 | In Family F2, there are more than 4 children born on the same day: I5(Emily /Mao/), I14(Emilya /Mao/), I15(Emilyb /Mao/), I16(Emilyc /Mao/), and I17(Emilyd /Mao/). | Passed
AT89 | US27 | Multiple births rule | In Family F2, only child I1 was born on 27 JAN 1970 | No error message | Passed
Note on E22: Yanjun:

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2015-02-25 | 30 |  | 598
2015-03-01 | 24 | 6 | 1034 | 260 | 100.6154
2015-03-10 | 18 | 6 | 1303 | 130 | 124.1538
2015-03-29 | 12 | 6 | 1595 | 160 | 109.5
2015-04-12 | 6 | 6 | 1939 | 195 | 105.8462
#DIV/0!

## Sprint1
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Inexistent ID | AT01~AT07 | gc | Done | 150 | 60 | 98 | 60 | 2015-02-27
T01.01 | Check the existance of family IDs of every individual |  | gc
T01.02 | Link the existant family IDs to the related families |  | gc
T01.03 | Check the existance of individual IDs of every family |  | gc
T01.04 | Link the existant individual IDs to the related individuals |  | gc
US02 | Unmatched pointers | AT08~AT14 | gc | Done | 50 | 40 | 72 | 45 | 2015-02-28
T02.01 | Check if the family pointers of an individual point back to the individual(as the same role in the family) |  | gc
T02.02 | Check if the individual pointers of a family point back to the family(as the same role in the family) |  | gc
US03 | Invalid date | AT15~AT21 | yw | Done | 80 | 45 | 162 | 60 | 2015-03-01
T03.01 | Get current date(year, month, day) |  | yw
T03.02 | Get every date from stored structure |  | yw
T03.03 | check if the event date exists |  | yw
T03.04 | check if the event date of individual or family is after current date |  | yw
US05 | Death before birth | AT22~AT23 | yw | Done | 20 | 30 | 30 | 30 | 2015-03-01
T05.01 | Get individual's birth date |  | yw
T05.02 | Get individual's death date |  | yw
T05.03 | Check if individual's death is before birth
US04 | Invalid family members | AT24~AT26 | abg | Done | 80 | 45 | 44 | 45 | 2015-02-28
T04.01 | Find all the husbands and wives in each family |  | abg
T04.02 | count the amount of husbands and wives respectively |  | abg
T04.03 | check the amount is less, equal or greater than one |  | abg
US06 | Invalid gender | AT27~AT28 | abg | Done | 50 | 25 | 27 | 20 | 2015-03-01
T06.01 | Get the sex of a husband and the sex of a wife in a family |  | abg
T06.02 | check if the husband is a male and the wife is a female |  | abg
Review Results
Keep doing:
Meet at least twice a week
Inform everyone when you discover a problem
Modify the user stories we are about to implement next sprint to more proper and completed
Add more user stories if you come up new one
Avoid:
Forgetting to commit changes to GitHub

## Sprint2
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US07 | Invalid age of an individual | AT29~AT31 | gc | Done | 20 | 10 | 21 | 30 | 2015-03-07
T07.01 | Get the birth date of the individual |  | gc
T07.02 | Get the death date of the individual(if exist) |  | gc
T07.03 | Check the age of the individual |  | gc
US08 | Multiple roles in a family | AT32~AT33 | gc | Done | 50 | 30 | 72 | 30 | 2015-03-07
T08.01 | Get all the individuals of the family |  | gc
T08.02 | Sort the individuals by ID |  | gc
T08.03 | Check if some individuals play multiple roles in the family |  | gc
US09 | Invalid ages in a family | AT34~AT36 | YW | done | 50 | 45 | 42 | 15 | 2015-03-09
T09.01 | get access to each family record |  | YW
T09.02 | get each husband /wifebirth date |  | YW
T09.03 | get each child birth date |  | YW
T09.04 | compare husband/wife birth date with child birth date |  | YW
US10 | Death before marriage | AT37~AT38 | YW | done | 30 | 10 | 31 | 20 | 2015-03-09
T10.01 | get access to each family record |  | YW
T10.02 | if there is no marriage date then continue to next family record |  | YW
T10.03 | get each husband/wife death date |  | YW
T10.04 | if there is no death date then continue |  | YW
T10.05 | compare the death date with marriage date |  | YW
US11 | Marriage before birth | AT39~41 | abg | done | 30 | 10 | 31 | 25 | 2015-03-11
T11.01 | get the acess to each family record
T11.02 | If there is no marriage date then contine to the next family record
T11.03 | get husband and wife birth date
T11.04 | Compare the birth date with marriage date
US12 | Divorce before marriage | AT42~43 | abg | done | 30 | 10 | 15 | 10 | 2015-03-11
T12.01 | get the acess to each family record
T12.02 | If there is no marriage date and Divorce date then contine to the next family record
T12.03 | Compare the marrige date with divorce date
Review Results
Keep doing:
Meet at least twice a week
Inform everyone when you discover a problem
Modify the user stories we are about to implement next sprint to more proper and completed
Avoid:
Forgetting to commit changes to GitHub

## Sprint3
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US13 | Death before giving birth | AT44~46 | gc | done | 70 | 30 | 115 | 40 | 2015-03-24
T13.01 | Get the death date of the wife(if exists) in each family |  | gc
T13.02 | Compare the death date of the wife with the birth date of her each child |  | gc
T13.03 | Check if the wife died before she giving birth to some child |  | gc
T13.04 | Get the death date of the husband(if exists) in each family |  | gc
T13.05 | Add 10 months to the death date
T13.06 | Compare the fixed death date of the husband with the birth date of her each child |  | gc
T13.07 | Check if the husband died more than 10 months before his child was born |  | gc
US14 | Polygamy | AT47~48 | gc | done | 50 | 20 | 45 | 30 | 2015-03-24
T14.01 | Get the FAMS of each Individual |  | gc
T14.02 | Store the other spouse of each family if they do not divorce currently |  | gc
T14.03 | Check if the number of the stored spouses is greater than 1 |  | gc
US15 | Illegal spouse | AT49~50 | yw | done | 100 | 45 | 19 | 30 | 2015-03-27
T15.01 | get access to family record |  | yw
T15.02 | get record every child in each family |  | yw
T15.03 | compare each child to every other child in the same family |  | yw
T15.04 | check if two of the children have the same FAMS record which indicates that they are married |  | yw
T15.05 | It is illegal if two siblings get married |  | yw
US16 | Illegal marrige age | AT51~54 | yw | done | 30 | 10 | 24 | 25 | 2015-03-27
T16.01 | get access to each family record |  | yw
T16.02 | get the marriage date of this family |  | yw
T16.03 | get birth date of both husband and wife |  | yw
T16.04 | subtract the marriage date by the birth date to get the age when husband of wife got married |  | yw
T16.05 | It is not allowed if the husband gets married under 20 nor wife gets married under 18 |  | yw
US17 | Amount of family members | AT55~56 | abg | done | 20 | 10 | 9 | 10 | 2015-03-29
T17.01 | Get each family record
T17.02 | In family record get the count of husband , wife and child
US18 | Age gap among the children | AT57~58 | abg | done | 50 | 20 | 34 | 25 | 2015-03-29
T18.01 | get access to each family record
T18.02 | get record every child in each family
T18.03 | Compare their birth date
Review Results
Keep doing:
Meet at least twice a week
Inform everyone when you discover a problem
Modify the user stories we are about to implement next sprint to more proper and completed
Avoid:
Forgetting to commit changes to GitHub

## Sprint4
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US19 | Pregnancy limit | AT73~74 | abg | done | 50 | 25 | 30 | 25 | 2015-04-12
T19.01 | Check the family record
T19.02 | get the wife age and children age
T19.03 | Compare the ages between 18to 50
US20 | Child in family | AT59~60 | gc | done | 75 | 30 | 15 | 30 | 2015-04-06
T20.01 | Get the pointers of famc for each individual |  | gc
T20.02 | Check if the size of pointers is greater than 1 |  | gc
US21 | Family rule | AT77~78 | yw | done | 100 | 50 | 11 | 10 | 2015-04-12
T21.01 | get access to each individual record |  | yw
T21.02 | read every individual's famc and fams record |  | yw
T21.03 | if an individual doesn't have a famc nor a fams record, then he/she doesn't belong to any family |  | yw
US22 | Completed information | AT79~85 | yw | done | 70 | 35 | 30 | 20 | 2015-04-12
T22.01 | get access to each individual record |  | yw
T22.02 | if an individual's name, sex or birthday record is null, then he/she doesn't complete his/her information |  | yw
T22.03 | get access to each family record |  | yw
T22.04 | if a family doesn't have a marriage record, then this family doesn't complete its information |  | yw
US23 | Divorce before giving birth | AT75~76 | abg | done | 75 | 30 | 20 | 20 | 2015-04-12
T23.01 | get the acess to each family record
T23.02 | If threr is no divorce date continue to the next family
T23.03 | Compare the Birth date with divorce date
US24 | Unique information | AT61~72 | gc | done | 100 | 45 | 226 | 90 | 2015-04-06
T24.01 | Scan all the tags in the file |  | gc
T24.02 | For the tags within each INDI tag, count the numbers of NAME, SEX, BIRT DATE and DEAT DATE |  | gc
T24.03 | For each individual, check if the numbers of NAME, SEX and BIRT DATE are all 1, and if the number of DEAT DATE is 0 or 1 |  | gc
T24.04 | For the tags within each FAM tag, count the numbers of MARR DATE and DIV DATE |  | gc
T24.05 | For each family, check if the number of MARR DATE is 1, and if the number of DIV DATE is 0 or 1 |  | gc
Review Results
Keep doing:
Meet at least twice a week
Inform everyone when you discover a problem
Modify the user stories we are about to implement next sprint to more proper and completed
Avoid:
Forgetting to commit changes to GitHub

## Sprint5
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US25 | Last name rule | AT86~87 | gc | done | 30 | 35 | 31 | 30 | 2015-04-20
T25.01 | For each family, get the last name of the husband. |  | gc
T25.02 | Get the last names of the children |  | gc
T25.03 | Check if the last names of husband and children are the same |  | gc
US26 | Birth date limitation |  | abg |  | 15 | 30
US27 | Multiple births rule | AT88~89 | gc | done | 35 | 70 | 43 | 50 | 2015-04-20
T27.01 | For each family, get the birthdays of all the children |  | gc
T27.02 | Count the numbers of children that were born on the same day |  | gc
T27.03 | Check if there are more than 4 children born on the same day in one family |  | gc
US28 | May-December marriage |  | abg |  | 20 | 15
US29 | Given birth before marriage |  | yw |  | 35 | 40
US30 | Marriage rule |  | yw |  | 30 | 35